## Jira Export Excel CSV (all fiel
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Custom field (Actual end) | Custom field (Actual start) | Custom field (Category) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Checklist Completed) | Custom field (Checklist Content YAML) | Custom field (Checklist Progress) | Custom field (Checklist Progress %) | Custom field (Checklist Text) | Custom field (Checklist Text (view-only)) | Custom field (Department) | Custom field (Department)_1 | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Link) | Epic Link Summary | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Goals) | Custom field (Google Drive attachments) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Project overview key) | Custom field (Project overview status) | Custom field (Rank) | Custom field (Request Type) | Custom field (Request participants) | Custom field (Sentiment) | Sprint | Custom field (Start date) | Custom field (Story Points) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Total forms) | Custom field (Vulnerability) | Custom field ([CHART] Date of First Response) | Custom field ([CHART] Time in Status) | Parent | Parent summary | Status Category | Status Category Changed
Proper Error handling | CMP-39 | 10516 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:23 | 2025-01-06 19:50 | 2025-01-06 19:56 |  |  | 0 | While performing a transaction, it failed and I couldn't tell whether its an issue of wrong passphrase or something else. Please plugin team fix this. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001ze:r |  |  |  | CMP Sprint 3 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:23
Proper error handling of failing transactions | CMP-35 | 10510 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-16 20:49 | 2025-01-06 19:50 | 2025-01-06 19:56 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001z7: |  |  |  | CMP Sprint 3 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-16 20:49
Receive Transaction Confirmations | CMP-18 | 10394 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-05-13 14:09 | 2025-01-06 19:46 | 2025-01-06 19:56 |  |  | 0 | As a user, I need to receive confirmations for transactions so that I can be assured of their success and proceed with subsequent operations within the Mendix application |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-10 | Query the chain | [10 empty] | 0¦i001ze:v |  |  |  | CMP Sprint 3 | [11 empty] | 10376 | Query the chain | To Do | 2024-05-13 14:09
Wallet Security Features | CMP-14 | 10390 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-05-13 13:52 | 2025-01-06 19:45 | 2025-01-06 19:56 |  |  | 0 | As a developer, I need to integrate advanced security features, such as encryption and multi-factor authentication, to protect wallet data on both the server and client sides. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-1 | Cardano Wallets Integration | [10 empty] | 0¦i001ze:i |  |  |  | CMP Sprint 3 | [11 empty] | 10362 | Cardano Wallets Integration | To Do | 2024-05-13 13:52
Implement Smart Contract Interactions | CMP-8 | 10374 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-04-30 21:02 | 2025-01-06 19:44 | 2025-01-06 19:56 |  |  | 0 | As a developer, I need to enable users to interact with smart contracts directly from the Mendix platform, ensuring that these interactions are secure and efficient. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-4 | Transaction handling | [10 empty] | 0¦i001ze: |  |  |  | CMP Sprint 3 | [11 empty] | 10370 | Transaction handling | To Do | 2024-04-30 21:02
Integrate Native Token Transactions | CMP-7 | 10373 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-04-30 21:02 | 2025-01-06 19:44 | 2025-01-06 19:56 |  |  | 0 | As a developer, I want to provide support for creating and managing transactions involving native tokens, not just ADA, within the Mendix environment |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-4 | Transaction handling | [10 empty] | 0¦i001zd: |  |  |  | CMP Sprint 3 | [11 empty] | 10370 | Transaction handling | To Do | 2024-04-30 21:02
Support Multi-Signature Transactions | CMP-6 | 10372 | Story | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-04-30 21:02 | 2025-01-06 19:44 | 2025-01-06 19:56 |  |  | 0 | As a developer, I need to implement the capability for users to create multi-witness transactions to enhance security and meet complex transaction requirements. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-4 | Transaction handling | [10 empty] | 0¦i001zb: |  |  |  | CMP Sprint 3 | [11 empty] | 10370 | Transaction handling | To Do | 2024-04-30 21:02