## Jira Export Excel CSV (all fiel
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Custom field (Actual end) | Custom field (Actual start) | Custom field (Category) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Checklist Completed) | Custom field (Checklist Content YAML) | Custom field (Checklist Progress) | Custom field (Checklist Progress %) | Custom field (Checklist Text) | Custom field (Checklist Text (view-only)) | Custom field (Department) | Custom field (Department)_1 | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Link) | Epic Link Summary | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Goals) | Custom field (Google Drive attachments) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Project overview key) | Custom field (Project overview status) | Custom field (Rank) | Custom field (Request Type) | Custom field (Request participants) | Custom field (Sentiment) | Sprint | Custom field (Start date) | Custom field (Story Points) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Total forms) | Custom field (Vulnerability) | Custom field ([CHART] Date of First Response) | Custom field ([CHART] Time in Status) | Parent | Parent summary | Status Category | Status Category Changed
close button doesn't do anything. | CMP-47 | 10524 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:49 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0021v: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:49
Startup experience | CMP-46 | 10523 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:48 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | Seeing just the Landano logo at startup might be confusing for new users. What about: "Cardano Mendix plugin - by Landano" |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0021n: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:48
"Select Network" label is not clear | CMP-45 | 10522 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:47 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | At this stage we are asked to perform a transaction with out wallet. We have already selected the Network in the previous step. This looks like it should be labelled "Select transaction type" |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0021f: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:47
Transaction workflow has "Create Wallet" header | CMP-44 | 10521 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:46 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | the top level header should change from "Create Wallet" to "Create Transaction" |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i00217: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:46
Wallet should show opening balance | CMP-43 | 10520 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:46 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | It was not clear what testADA balance, if any, my preprod wallet had so I wasn't sure what I could send. I also did not have a test wallet address to send the funds to. I don't know another wallet key to use so have to stop here. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0020z: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:46
My Awesome Cardano Transaction | CMP-42 | 10519 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:41 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | get rid of the autofill text under message metadata, i appreciate the informality but i don't think any autofill should be here. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0020r: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:41
step labels | CMP-41 | 10518 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:41 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | for me it would be helpful to have more descriptive step labels, to know what's happening. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0020j: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:41
grammar | CMP-40 | 10517 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:25 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | unlock is one word |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i0020b: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:25
Design and Layout Not Adjusted Based On Figma | CMP-38 | 10515 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 18:22 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | The design and layout isn't adjusted based on my figma design. - Colors of wallets are harsh green - Base address and stake address should be copiable with a button - No information given in transactions whether it momeu was received or sent. as well the amount received or sent isn't displayed, you only see and adjusted balance after refresh |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001zv: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 18:22
Typo and Unclear what certain functions do | CMP-37 | 10514 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 12:56 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | Un lock transaction hash has a typo not sure what lock transaction hash or unlock transaction hash does. We should add a helper to this |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001zn: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 12:56
Confusion on this page | CMP-36 | 10513 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2025-01-06 12:44 | 2025-01-06 19:49 | 2025-01-06 18:49 |  |  | 0 | Besides the fact that the typography doesn't allow to grasp hierarchy of information, it also is unclear what this page does. Questions: - Why is the title Treasury if it's called multi-sign in nav bar - what is script hash - Why are the words Required in large text - Mandate, what is that, no description given. Assumption would be rules for multi-sign smart contract. - 2 search buttons on screen with no info given. I know on click of left one a search box appears for script hash search, but still don't know what that means. More description text is needed - Don't understand what button "Reset" will do, reset what, wording should be clearer. - Transactions new delete and sign. This should be grouped seperately from the rest, layout should be redesigned. And it should be on top of page. Then theres also the button create transaction, which I thought was for the button "New" under transactions. |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001zf: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2025-01-06 12:44
Metadata capped at 64 characters | CMP-34 | 10509 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-16 20:48 | 2025-01-06 19:49 | 2024-12-16 20:48 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001yz: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-16 20:48
edit and correct this text | CMP-31 | 10506 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-15 20:25 | 2025-01-06 19:49 | 2024-12-15 20:25 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001yb: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-15 20:25
refresh button : make it more obvious! | CMP-30 | 10505 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-15 20:24 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001y3: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-15 20:24
wallet address not receive test ada | CMP-27 | 10502 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-15 18:48 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 | i did not receive test ada into the wallet. first time, the transaction did not register, the hash had no record attached to it. second attempt, the hash revealed a transaction, but the ada never arrived in the wallet. UPDATE: the ada was sent to the stake wallet, but never showed up as a balance here in sandbox. here's the hash for the second transaction: 8e6624ee692e640022391f8c651732f4be9f307ab02ce21beb6518ea274cc3fc |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001xf: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-15 18:48
add copy buttons for the base and stake addresses | CMP-25 | 10500 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-15 18:47 | 2025-01-06 19:49 | 2025-01-06 20:49 |  |  | 0 |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001wz: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-15 18:47
Consider creating a copy button | CMP-24 | 10499 | Bug | To Do | CMP | Cardano Mendix-Plugin | software | Dorus van der Kroft | 622f42c475f257006a98fc2a |  | Medium |  |  |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | Dorus van der Kroft | 622f42c475f257006a98fc2a | 2024-12-15 18:38 | 2025-01-06 19:49 | 2025-01-06 19:50 |  |  | 0 | A copy button would save time and also ensures that the address is copied correctly |  | Dorus van der Kroft | 622f42c475f257006a98fc2a | [17 empty] | 0 | [6 empty] | CMP-48 | Feedback Handling | [10 empty] | 0¦i001wr: |  |  |  | CMP Sprint 4 | [11 empty] | 10525 | Feedback Handling | To Do | 2024-12-15 18:38